## Sheet1
Site Code | Description | Postcode | Proposed Investment (£) | Investment Programme | Year/Timescale of capital investments | Comment/Status
SIT0116 | BRUNSTANE PRIMARY SCHOOL & NURSERY AND MAGDALENE COMMUNITY CENTRE | EH15 3BE | 594092 | Asset Management Works Programme | 2019/20 | Commissioned and out to tender. Expect works to commence summer 2019
SIT0586 | JEWEL HOUSE HOME FOR OLDER PEOPLE | EH15 3JZ | 170656 | Asset Management Works Programme | Completed 2018/19 | Completed 2018/19
SIT0770 | NEWCRAIGHALL PRIMARY SCHOOL & NURSERY | EH21 8 | 1250000 | Asset Management Works Programme | Programme 2020/21 | Commission drafted and being reviewed
SIT0872 | PORTOBELLO/JOPPA FORESHORE (PORTOBELLO SWIM CENTRE) | EH15 1 | 2980000 | Asset Management Works Programme | 2019/21 | This work will span over 2 financial years. Partly commissioned, works in 2019/20 has an approx. value of £720,000
SIT1095 | TOWERBANK PRIMARY SCHOOL & NURSERY | EH15 1 | 570000 | Asset Management Works Programme | 2019/20 | Commissioned and out to tender. Expect works to commence summer 2019
| TOTAL FOR AMW PROGRAMME |  | 5564748
SIT0181 | CASTLEBRAE HIGH SCHOOL | EH16 4 | 32592085 | Capital Investment Programme | New School Proposed | In design stage
SIT1423 | NEW PORTOBELLO HIGH SCHOOL | EH15 3BY | 32400500 | Capital Investment Programme | Completed 2017 | Recent new High School
SIT1656 | NEW ST JOHN's PRIMARY SCHOOL |  | 11300000 | Capital Investment Programme | Completed 2018/19 | Recent new Primary School. (Strictly speaking this school is located in the Craigentinny/Duddingston ward)
| TOTAL FOR CIP PROGRAMME |  | 76292585